Construction Management Applications: Challenges in Developing Execution Plans
Presented by:
 Amlan Mukherjee
and
Nilufer Onder
Michigan Technological University
May 14, 2010 --- ICAPS, Toronto

---
Construction Management Domain
- To build ... under constraints
  - Time
  - Budget
  - Site location
  - Resources: equipment, labor, material
- To avoid or contain ... contingencies
  - Adverse weather
  - Accidents
  - Delivery problems
  - Labor strikes
[Speaker Notes: Constraints obviously are important because they define how to respond to contingencies. Now we will show how the plans are constructed and where the constraints are established.]

---
Our objective
Provide automated project management support for
  - Project execution
  - What-if analysis
  - Contingency planning

---
Stages of Steel Project Management
Design decision
to use steel
Develop contract
documents
Design
development
Bidding
General contract
award
Participants
Owner
Architect
Structural engineer
General contractor
Construction manager
Design builder
Steel contractor
Steel fabricator
Steel erector
Lower tier
 subcontractors
Steel suppliers
Detailers
Steel contract
execution
Order steel
Prepare erection
& shop drawings
Award lower
tier subcontracts
Deliver material
Shop drawing
approval
Shop drawing
approval
Fabricate steel
Deliver
fabricated steel
Deliver
Erect fabricated
steel
[Speaker Notes: Explain a few of those and show the floor plan example later. The small boxes on the lower right hand side are blown up on the next slide. Tell a bit about the responsibilities of a few participants.]

---
Stages of Steel Project Management (cont’d)
Steel contract
execution
Order steel
Prepare erection
& shop drawings
Award lower
tier subcontracts
Deliver material
Shop drawing
approval
Participants
Owner
Architect
Structural engineer
General contractor
Construction manager
Design builder
Steel contractor
Steel fabricator
Steel erector
Lower tier
 subcontractors
Steel suppliers
Detailers
Shop drawing
approval
Fabricate steel
Deliver
fabricated steel
Deliver
Erect fabricated
steel
[Speaker Notes: This is the rest of the process. Tell a bit more about the box that we are most interested in.]

---
Structural Framing Plan
[Speaker Notes: This is a representative structural framing plan. It shows the first floor.]

---
Corner of the floor
[Speaker Notes: This page shows the zoomed in corner of the plan on the previous page. Show the I-beams, C-beams tell about how they are placed with respect to the wind direction and so on. Tell that there are many ways to operationalize this plan.]

---
The schedule

---
Contingencies – Planning error

---
Contingencies – Productivity changes

---
Contingencies – Material not delivered
[Speaker Notes: Space is not a concern]

---
Contingencies – Space is a concern

---
The big picture

---
Current Abilities & Future Needs
- Current Abilities
  - Gantt charts, critical path method (CPM)
  - Linear scheduling (Ioannou et al.)
  - Simulation of operations (AbouRizk et al.)
  - Virtual/Augmented reality (Martinez, Kamat et al.)
- Resource/resource to human/resource interactions:
  - Decision-making at a system-level
  - Constraint driven approaches
  - Contingency planning

---
Our system
- ICDMA (Interactive Construction Decision Making Aid)
- Can perform what-if analysis on As Planned Schedules (APSs) if provided with
  - Tasks and dependencies
  - Relevant constraints
  - External events
  - Relevant effects of events such as productivity

---
ICDMA interface
[Speaker Notes: User takes role of managing construction projects. User is the decision maker.]

---
Temporal Network with Activities and Events (TONAE)
A1,E
A1,B
E1,B
E1,E
A2,E
A2,B
Y2
A3,B
A4,E
A4,B
T1
T2
T3
T4
T5
TNOW
0
0
6
0
1
1
1
1
0
1
[Speaker Notes: We represent the constraints. Bolting cannot begin until hoisting is complete. Decking cannot begin until bolting is half complete. We throw in stochastic events]

---
Monte Carlo Simulations
Ti
Ti+1
Ti+2

---
Extend ICMDA with contingency planning
- When the execution deviates from the as-planned schedule (APS), automatically suggest alternatives
- Assumptions of automated planners
  - The domain information is represented in PDDL format
  - There is a single plan
  - All planning activities are done “offline”
[Speaker Notes: PDDL format: action based, precondition-effect Floor plans are not like that To do this, we need to be able to relax the following assumptions Single plan: There are general guidelines as to what to do but there are many ways to translate to a sequence of actions Offline: Some actions have already been executed Information is not stored]

---
Challenge 1:
knowledge representation
- Knowledge:
  - Dispersed, multi-format
  - Incomplete operationalization
- Need to represent:
  - The project plans and schedules
  - Constraints
  - Stochastic events
[Speaker Notes: Dispersed, multi-format: in engineering domains the design knowledge is pretty complete Incomplete: but there are many ways to operationalize the plans in drawings. Therefore, the plan knowledge is incomplete. There is a large space of possible contingencies. They are considered as a lumpsum (contingency funds) without paying attention to individual events.]

---
Challenge 2: execution time deviations
- Need to consider:
  - Effects on the cost and the duration
  - Constraints that are violated
  - Soft constraints
- Show:
  - Various levels of detail
    (HTN-style, macro-style)
  - Different views to stakeholders

---
Challenge 3: contingency responses
- Possible responses:
  - Do nothing (use contingency funds)
  - Reschedule, reallocate
  - Replan
- Available technologies
  - Plan generation
  - Planning under uncertainty
  - Planning with constraints
[Speaker Notes: There are multiple plans, executors Participants: We currently don’t need Figure 1-3 on page 14 (Lines of responsibility on a steel project) We need to point out that this is a “plan” prepared by and executed by many different participants. PDDL is single executor.The different executors are bringing in constraints to related plans. The devil is in the details... If all the details are represented at once, planning will be difficult. The specific contingency should help focus the system.]

---
Conclusion
- Construction management:
  knowledge-rich domain
- Challenge 1: knowledge representation to aid contingency responses
- Challenge 2: Understanding the contingencies
- Challenge 3: Responding to contingencies

---
Thank You!
Acknowledgments
NSF #SES0624118

---
Additional References
- Ansari, Alex. “Target Costing: When the Client Looks Under the Hood,” Constructor, p. 64, March/April 2010.
- Mrozowski, Tim, Matt Syal, and Syed Aqeel Kakakhel. “Construction Management of Steel Construction: Project Management Module,’’ Technical Report, American Institute of Steel Construction (AISC), 1999.
[Speaker Notes: These were used for the talk. They were not cited in the paper.]